UNITED STUDENTS DEVELOPMENT NETWORK (USDN)

ANNUAL PERFORMANCE & FINANCIAL REPORT 2025

Empowering Liberia's Youth: Education, TVET, Mentorship & Narcotic Drug Prevention
Headquarters: Methodist Compound, Congo Town Back Road, Monrovia, Liberia

EXECUTIVE HIGHLIGHT: Financial Snapshot 2025: Operating Budget of $400,000 USD successfully executed with a 95.8% fund utilization rate across 4 major program pillars, impacting over 3,500 students and youth across Liberia.

1. Executive Summary & Leadership Statement

1.1 Message from the Founder & Executive Director

In 2025, the United Students Development Network (USDN) marked another historic milestone in our journey toward building a resilient, empowered, and skilled youth population in Liberia. Established in 2023, USDN has grown from a grassroots youth initiative into a nationally recognized non-profit organization dedicated to closing academic gaps, expanding technical and vocational education, and protecting our young people from the devastating impacts of substance abuse.

With an annual operating budget of $400,000 USD in 2025, supported by generous donors, institutional partners, and mobile money contributors, USDN expanded its footprint across Montserrado County and neighboring communities. Through disciplined fiscal management, robust monitoring frameworks, and the unwavering commitment of our volunteer mentors and tutors, we successfully transformed thousands of lives.

1.2 About USDN

• Mission: To empower Liberia's youth through holistic education, mentorship, vocational skills training, and health awareness, fostering academic excellence and social responsibility.
• Vision: A nation where every young person has equitable access to quality education, career opportunities, and a supportive, drug-free environment to thrive.
• Core Values: Integrity, Accountability, Inclusivity, Excellence, and Community Impact.

2. Key Programmatic Achievements & Performance Metrics

In 2025, USDN structured its operations under four primary program pillars designed to address the interconnected challenges facing Liberian youth:

| Program Pillar | Key Activities & Scope | Target Beneficiaries | 2025 Achievements |
| --- | --- | --- | --- |
| Investing in Education | Academic tutoring, WASSCE prep, literacy programs & supply distribution | High school & elementary students | 1,250 students tutored; 88.5% WASSCE pass rate among beneficiaries |
| Championing Mentorship | Peer-to-peer coaching, leadership bootcamps, career guidance | Youth aged 12–24 years | 450 active mentorship matches; 12 regional workshops conducted |
| Technical & Vocational Training (TVET) | Computer literacy, electrical wiring, tailoring, small business management | Unemployed & out-of-school youth | 620 youth enrolled; 510 certified graduates with starter kits |
| Narcotic Drug Prevention & Psychosocial Support | Community awareness rallies, school outreach, confidential counseling | Vulnerable urban youth & students | 1,800 youth reached; 140 receiving ongoing psychosocial counseling |

3. Financial Report & Budget Execution ($400,000 USD)

USDN maintains rigorous financial oversight, transparency, and internal control systems. For the fiscal year ending December 31, 2025, USDN operated on a total budget of $400,000 USD. Funding was secured through institutional grants, corporate social responsibility (CSR) sponsorships, community donations, and mobile money giving.

3.1 Revenue Breakdown

| Funding Source | Description | Amount (USD) | Percentage (%) |
| --- | --- | --- | --- |
| Institutional & Partner Grants | International & domestic development partner grants | $220,000 | 55.0% |
| Corporate CSR Sponsorships | Private sector and telecom partnership contributions | $95,000 | 23.8% |
| Community & Individual Donors | Philanthropic contributions and executive giving | $55,000 | 13.8% |
| Mobile Money & Orange Money | Public digital fundraising (MTN MoMo & Orange Money) | $30,000 | 7.4% |
| Total Revenue | Fiscal Year 2025 Total Funding | $400,000 | 100.0% |

3.2 Expenditure Breakdown by Program Allocation

| Budget Category | Approved Budget | Actual Expenditure | Variance / Execution Rate |
| --- | --- | --- | --- |
| Investing in Education & Academic Tutoring | $110,000 | $106,400 | 96.7% executed |
| TVET & Skill Acquisition Centers | $120,000 | $117,200 | 97.7% executed |
| Narcotic Drug Prevention & Counseling | $70,000 | $66,800 | 95.4% executed |
| Championing Mentorship & Youth Leadership | $45,000 | $43,100 | 95.8% executed |
| Administrative, Logistics & Operations | $40,000 | $38,500 | 96.3% executed |
| Monitoring, Evaluation & Audit | $15,000 | $11,200 | 74.7% executed |
| Total Operating Expenses | $400,000 | $383,200 | 95.8% Overall Execution |

4. Operational Challenges & Strategic Mitigation

While 2025 delivered remarkable achievements, USDN navigated several operational challenges:
1. High Demand vs. Facility Capacity: Demand for TVET programs in Congo Town and surrounding areas exceeded available workshop equipment and seats. Mitigation: Implemented shift-based training schedules to maximize equipment usage.
2. Pervasive Drug Stigma: Victims of substance abuse initially resisted center-based counseling due to community fear. Mitigation: Expanded field-based mobile counseling teams and confidential street outreach.
3. Transportation & Logistics: Transportation costs for volunteer mentors traveling to remote communities posed financial burdens. Mitigation: Allocated stipend subsidies within the revised Q3 operating budget.

5. Strategic Outlook & 2026 Expansion Plan

Building on the success of 2025, USDN has outlined clear priorities for 2026:
• Regional Expansion: Extend mentorship and drug awareness programs beyond Montserrado County into Grand Bassa and Margibi counties.
• TVET Innovation Center: Establish an upgraded digital skills lab featuring basic coding, graphics, and mobile phone repair.
• Sustainable Funding: Scale up digital mobile money giving and establish long-term institutional partnerships.

6. Ways to Partner & Support USDN

USDN welcomes individuals, corporate bodies, and international organizations to join this transformative journey. Contributions directly fund student scholarships, vocational starter kits, and drug prevention outreach.

DONATION & PARTNERSHIP CHANNELS: Official Mobile Giving Channels: • Lonestar Cell MTN Mobile Money: 0760591331 • Orange Money Liberia: 0886859315 Headquarters: Methodist Compound, Congo Town Back Road, Monrovia, Liberia Website / Contact Platform: www.kemoonenterprise.org / USDN Portal